## CONTACTS
[Your Event] Contacts
Section | Who | Name | What for | Phone | Email
Below is an example of how to add details on all of the contacts involved in your event's delivery - this will ensure that all contacts are in one place so that you can find them during the chaos of event delivery.
EXECUTIVE TEAM |  | Event | Coordinator
BAR | Liquor Licence |  | Licencing
BAR | Bar suppliers |  | Supply beer at cost
KIDS ENTERTAINMENT |  |  | Sponsorship
KIDS ENTERTAINMENT | Facepainter
ENTERTAINER |  |  | Celebrity chef
ENTERTAINER |  |  | Celebrity gardener
MARKETING |  |  | Advertising
MARKETING |  |  | Sponsorship
MC |  |  | Audio visual
OPERATIONS | Water truck |  | Stop dust on the road
OPERATIONS | Portable toilets |  | Portaloos
OPERATIONS | Event hire |  | Marquees
OPERATIONS | Sand supplier for kids sandpit |  | Sand
OPERATIONS | Road corridor Permit |  | Traffic
SUSTAINABILITY |  |  | Recycling
VOLUNTEERS |  |  | Printing of volunteer lanyards

## EVENT DELIVERY DAYS
The content in the framework below is an example for a one day food festival - delete the content and update the template for your event.
AREA RESPONSIBLE | KEY TASK & MILESTONES | TIMELINE | ✔ | IS A RUN SHEET REQUIRED?
Bar | Be onsite to ensure marquee, ice trough and tables are set up on level ground | Day before event
Bar | Be on site for the delivery of beer and wine and do a stock take to ensure it is all there | Day before event
Bar | At the end of the day do a stocktake - make notes of this for the post event report. Collate what is left over and determine what sold best, what didn't sell well and provide recommendations for next year's event | Day of event
Bar | Set up the stall and decorate, ensuring that RSA and licensing signage is displayed according to guidelines | Day of event
BBQ | At the end of the day do a stocktake of what meat is left over and store it in the cold room. Make notes on this for the post event report. Use leftovers for the volunteer thank you BBQ. | Day of event
BBQ | Coordinator is responsible for ensuring that all volunteers are adhering to the food safety guidelines | Day of event
BBQ | Ensure food handling guidelines are on display, and that soap and hand towels are available for handwashing | Day of event
BBQ | Manage the stall and volunteers - the coordinator should not commit to a role on the day (e.g. cooking) | Day of event
BBQ | Ensure that no food is consumed by volunteers near the BBQ area - ensure they go to the staff area for meals | Day of event
CHILDREN | Set up the kids activities | Festival Weekend
CHILDREN | Coordinate volunteers, answer questions and assist children | Day of event
EXECUTIVE TEAM | Coordinatre and oversee the smooth flow of the dinner event | Day before event |  | Yes - Refer Gala Dinner Run Sheet
EXECUTIVE TEAM | Monitor flow of visitors through the site and queues to make changes for next year | Festival Weekend
EXECUTIVE TEAM | Surveys | Day of event
FINANCE | Introduce the finance team to all the stall coordinators at the start of the day | Day of event
FINANCE | Work with the Stallholder Coordinator to invoice and receive stallholder payments. Send receipts to the Stallholder Coordinator and follow up on late payments | Ongoing
MAIN MARQUEE | Hang sponsorship signage | Day before event
MAIN MARQUEE | Set up and decorate marquee | Day before event
MARKETING | Load survey forms to the website | Festival Weekend
MC | Pre check with sound people well before the 9am start on Sunday | Day before event
MC | Set up all sound gear on Saturday | Day before event
MC | Communicate regularly with stalls re stock and make relevant announcements throughout the day | Day of event
MC | Achieve balance between getting the announcements out and burdening attendees with noise | Day of event
MC | Do all the outside announcements from 9am to 4pm | Day of event
MC | Ensure celebrities are at the correct locations at the correct times for outside events | Day of event
MERCHANDISE | Deliver selected merchandise at other strategic places around the festival site - e.g. bar for stubby holders, insulated bags with stalls selling product to keep cold - as pre arranged with relevant coordinators previously | Day before event
MERCHANDISE | Stocktake at end of the day - make notes for post event report | Day of event
MUSIC | Set up signage and any decorations | Day before event
MUSIC | Direct performers to the stage and ensure they have water and everything they need | Day of event
MUSIC | MC the music tent, ensuring a good flow of music throughout the day | Day of event
OPERATIONS | Ensure Stallholder Coordinator has enough Walkie Talkies for all volunteers | Day before event
OPERATIONS | Coordinate the set up and pull down of fencing and signage once the traffic management role has been completed. | Festival Weekend
OPERATIONS | Coordinate the bump in of all infrastrsucture on site | Festival Weekend
OPERATIONS | Collect the lunch for the SES at the time agreed with BBQ coordinator | Day of event
OPERATIONS | Coordinate any communication between SES and MC during the day. Hold a debrief meeting with SES staff and volunteers once it is clear that the traffic management role has been completed on the day. | Day of event
STALLHOLDERS | Mark out the site with site numbers | Day before event
STALLHOLDERS | Liaise with electrician – ensure all power requirements are safe and working | Festival Weekend
STALLHOLDERS | Ensure stallholders are settled, setup and vehicles are off site by 8am | Day of event
STALLHOLDERS | Mark off stallholders as they arrive | Day of event
STALLHOLDERS | Set up and monitor the smooth flow of presenters into the marquee - ensure it is kept clean and tidy between presentations and ensure speakers are briefed 15 minutes before their talk | Day of event
STALLHOLDERS | Monitor stalls during the day – check they are happy and are selling what was agreed to. Get feedback from stalls during the day. Note general feel from the stallholders | Day of event
STALLHOLDERS | Check the list of goods intended to be sold by the stall holder listed on their application form – refuse any products if they don’t fit in with values of the event eg craft, product not made by stallholder or multi components eg coffee, biscuits, preserves etc. | Ongoing
VOLUNTEERS | Reallocate volunteers to areas if necessary - ensuring everyone has adequate support | Festival Weekend
VOLUNTEERS | Hand out lanyards for volunteers as they arrive | Festival Weekend
VOLUNTEERS | Coordinate floaters and roamers and be a support person during the day…. | Day of event
VOLUNTEERS | Ensure stalls/coordinators have enough helpers | Day of event
VOLUNTEERS | Coordinate volunteer roster at informaion tent | Day of event

## EXAMPLE_DINNER EVENT RUN SHEET
Gala Dinner - DATE - TIME - LOCATION
| Activity | Who | Requirements | Notes
Pre arrival
5pm (arrival) | Greet guests at the door |  |  | Ensure that someone is ready to personally look after sponsors and VIPs
5.30pm | Oyster Bar opens
6pm | MC asks all guests to be seated for the dinner | MC | Audio, table seating plan, ushers to move people from stnading bar and oyster area to seated area.
6.10pm | Welcome to Country
6.20pm | Official welcome by Mayor
6.30pm | Entrée served with gentle background music
7.00pm | Main meal served and head chef to talk to everyone about the produce used | Chef, kitchen staff, MC
8.00pm | Dessert served
8.30pm | Live band to commence entertainment
10.00pm | Last drinks and event wrap up

## EXAMPLE_WORKSHOP RUN SHEET
Workshops DAY 1 - DATE - TIME - LOCATION
| Activity | Who | Requirements | Notes
Pre arrival
9am
10am
11am
12pm
1pm
2pm
3pm
4pm