## Phases
Phase | Activities | Channels Used | Suggested Messages
1: Pre-Event Awareness 10 - 6 months prior | Building targeted reach and awareness quickly | Organic social media | Save the date in your calendar
| Artist and stallholder applications | Website
| Event information | Direct marketing (email and phone)
Content creation
2: Pre-Event Consideration 5 - 3 months prior | Targeted activity to an engaged audience | Digital advertising | How to get involved in this year’s festival (sponsor, volunteer, stallholder, entertainment)
| Sell tickets | Social media advertising
| Event information | Direct marketing | Promote key program elements
Influencer campaign
3: Pre-Event Conversion From 3 months prior | Tickets on sale and last chance messaging | Digital advertising | Tickets on sale
Book accommodation (link to options)
| News | Social media advertising | Itineraries (make a weekend of it)
| Drive FOMO (fear of missing out) | Direct marketing | Festival countdown – Top 10 great things about the festival (or Top 10 great things for eg families or campers or...)
| Sell tickets | PR & Media
|  | Traditional marketing (TV, print, radio) | Newsworthy item relevant to your event
Plan your weekend – itineraries, attractions, things to do
Preparing for the festival – weather, what to bring, maps/directions, program download
4: Event During event | Up to date info | Organic social media | User generated content (share photos posted on social media by others)
| User-generated content |  | Live Facebook videos
5: Post-Event Week after | Festival wrap | Organic social media | How it went (numbers of attendees/stallholders, images gallery, testimonial, etc)
| Highlights |  | Thank you to sponsors and volunteers
| Date for next year |  | Provide your feedback (link to survey in SurveyMonkey)

## Marketing Schedule
© Copyright rEVENTS Academy - Not for sale or distribution. All rights reserved.
BUDGET | Weeks to EVENT | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3
Week commencing (Sunday)
N/A | KEY EVENT DATES
100 Day Event Launch (Save the Date)
10 Week Countdown
Event Registration Opens
Tickets On Sale
Visitor Survey
EVENT WEBSITE | EVENT WEBSITE
100 Day Event Launch - site ready
Event Registration Opens
Tickets On Sale on website
Visitor Survey Link Live
Official Event Photos Live
Crosslink Social Media with Website
DIGITAL ADVERTISING | DIGITAL ADVERTISING
ORGANIC Social
Facebook
Instagram
Twitter/YouTube/Other
Online Advertising
Keyword research and SEO review
Social Advertising Campaigns
Website/Social Takeovers
Editorial Coverage
Banner Advertising
Email Newsletter
Sponsorship Proposals
Save the date
Event Registration Opens
General Event Promotion
Tickets On Sale
Event Evaluation Survey
NEWSPAPER ADVERTISING | NEWSPAPER ADVERTISING
Inserts
Program
1/4 Page Ads
Whats On at Event ad
Editorial Coverage
Media Releases
OUTDOOR ADVERTISING | OUTDOOR ADVERTISING
Distribution of Event Flyers
100 Day Launch
Street Banners
Town Entrance Signs
Product Placement (Flyers, Branded Bus Wraps)
RADIO/TV | RADIO/TV
Event Promotion
PR | PR
100 Day launch
FAMIL/hosting influencers/bloggers/ambassadors
Media Interviews
RETAIL & HOSPITALITY ACTIVATION | RETAIL & HOSPITALITY ACTIVATION
| Sponsorship Engagement | Prior to
Themed Shop Window Displays

## Awareness
Content Calendar
<<INSERT DATE FOR PERIOD>>
Activity | week | week | week | week | week | week
Key messages:
Important dates
WEBSITE/BLOG
Website
1-2 blogs per month
eDM
Media release
FACEBOOK
PAID
ORGANIC (5 posts per week)
Monday
Tuesday
Thursday
Sunday
INSTAGRAM (4per week)
1
2
3
4
OTHER
OTHER

## Consideration
Content Calendar
<<INSERT DATE FOR PERIOD>>
Activity | week | week | week | week | week | week
Key messages:
Important dates
WEBSITE/BLOG
Website
1-2 blogs per month
eDM
Media release
FACEBOOK
PAID
ORGANIC (5 posts per week)
Monday
Tuesday
Thursday
Sunday
INSTAGRAM (4per week)
1
2
3
4
OTHER
OTHER

## Conversion
Content Calendar
<<INSERT DATE FOR PERIOD>>
Activity | week | week | week | week | week | week
Key messages:
Important dates
WEBSITE/BLOG
Website
1-2 blogs per month
eDM
Media release
FACEBOOK
PAID
ORGANIC (5 posts per week)
Monday
Tuesday
Thursday
Sunday
INSTAGRAM (4per week)
1
2
3
4
OTHER
OTHER

## During
Content Calendar
<<INSERT DATE FOR PERIOD>>
Activity | week | week | week | week | week | week
Key messages:
Important dates
WEBSITE/BLOG
Website
1-2 blogs per month
eDM
Media release
FACEBOOK
PAID
ORGANIC (5 posts per week)
Monday
Tuesday
Thursday
Sunday
INSTAGRAM (4per week)
1
2
3
4
OTHER
OTHER

## Post
Content Calendar
<<INSERT DATE FOR PERIOD>>
Activity | week | week | week | week | week | week
Key messages:
Important dates
WEBSITE/BLOG
Website
1-2 blogs per month
eDM
Media release
FACEBOOK
PAID
ORGANIC (5 posts per week)
Monday
Tuesday
Thursday
Sunday
INSTAGRAM (4per week)
1
2
3
4
OTHER
OTHER